## Summary
Work Description | Total | Task | Grant | RPCs | Consultants | TOTAL
| Labor | Proportion | Funded | Grant-Funded | Sub-Grants | In-Kind
| 4250000 | 100% | 4250000 | 1287500 | 1250006.25 | 0
Scoping Phase | 127500 | 3% | 127500 | 0 | 95625 | 0
Task 1: Build Collaborative Partnerships | 255000 | 6% | 255000 | 0 | 191250 | 0
Task 2: Regional Resource Library and Scorecard | 850000 | 20% | 850000 | 323000 | 242250 | 0
Task 3: Conduct Public Engagement | 637500 | 15% | 637500 | 127500 | 95625 | 0
Task 4: Enhance Regional Leadership and Technical Capacity | 297500 | 7% | 297500 | 282625 | 211968 | 0
Task 5: Develop Regional Vision | 637500 | 15% | 637500 | 159375 | 119534 | 0
Task 6: Develop Regional Blueprint | 510000 | 12% | 510000 | 280500 | 207879.25 | 0
Task 7: Begin Implementation | 935000 | 22% | 935000 | 114500 | 85875 | 0

## HUD Work Plan
SE Florida Regional Vision and Blueprint Work Plan | [21 empty] | Where Are We Now? | [42 empty] | Where Are We Going? | [21 empty] | Where Do We Want To Go? | [27 empty] | How Do We Get There? | [31 empty] | How Do We Get There?
Detailed Tasks |  |  | 2011-02-01 |  |  |  | 2011-03-01 |  |  |  | 2011-04-01 |  |  |  | 2011-05-01 |  |  |  |  | 2011-06-01 |  |  |  | 2011-07-01 |  |  |  | 2011-08-01 |  |  |  |  | 2011-09-01 |  |  |  | 2011-10-01 |  |  |  |  | 2011-11-01 |  |  |  | 2011-12-01 |  |  |  | 2012-01-01 |  |  |  |  | 2012-02-01 |  |  |  | 2012-03-01 |  |  |  | 2012-04-01 |  |  |  |  | 2012-05-01 |  |  |  | 2012-06-01 |  |  |  | 2012-07-01 |  |  |  |  | 2012-08-01 |  |  |  | 2012-09-01 |  |  |  | 2012-10-01 |  |  |  |  | 2012-11-01 |  |  |  | 2012-12-01 |  |  |  |  | 2013-01-01 |  |  |  | 2013-02-01 |  |  |  | 2013-03-01 |  |  |  | 2013-04-01 |  |  |  |  | 2013-05-01 |  |  |  | 2013-06-01 |  |  |  | 2013-07-01 |  |  |  |  | 2013-08-01 |  |  |  | 2013-09-01 |  |  |  |  | 2013-10-01 |  |  |  | 2013-11-01 |  |  |  | 2013-12-01 |  |  |  |  | 2014-01-01 |  |  |  | 2014-02-01
|  |  | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 7 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 19 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
Scoping Phase |  |  | 2011-02-01 21: HUD Agreement; 2011-04-01 18: 60 Days; 2011-06-01 20: 120 Days
| Task S1 | Governance, Organization | bar: 2011-02-01 7 to 2011-05-01 9
| Task S2 | Work Plan Development | bar: 2011-02-01 21 to 2011-04-01 18
| Task S3 | Consortium Agreements | bar: 2011-04-01 4 to 2011-06-01 20
| Task S4 | Recruit Staff | bar: 2011-04-01 4 to 2011-04-01 25; 2011-05-01 23
| Task S5 | Form and Operationalize Work Groups and Committees | bar: 2011-04-01 18 to 2011-06-01 20
| Task S6 | Initiate Early Stages of Activities | bar: 2011-04-01 18 to 2011-06-01 20
| Task S7 | Develop RFP(s) | bar: 2011-05-01 23 to 2011-07-01 11
Governance and Consortium Building |  |  | 2011-09-01 26: Regional Summit - Peer Regions Presentation; 2012-02-01 20: Regional Summit - Existing Conditions and Trend Future; 2012-09-01 19: Regional Summit - Where Do We Want To Go?; 2013-04-01 8: Preferred Scenario - How Do We Get There?; 2014-01-01 20: Regional Vision Adoption - Regional Partnership
Regioinal Summits | bar: 2011-09-01 26; 2012-02-01 20; 2012-09-01 19; 2013-04-01 8; 2014-01-01 20
| Leadership Development, Identify Champions, Local Government Outreach |  | 2011-03-01 28: Convene Committee - Staff Positions - Draft Work Plan; 2011-04-01 18: Staff Position Approval; 2011-05-01 16: Final Committees & Work Plan Approval; 2011-06-01 13: Consortium Agreements RFP Approval; 2011-07-01 11: Interview & Appoint Consultant; 2011-07-01 25: Visioning exercise with Executive Committee; 2011-09-01 12: Summit Approval - Polling Results - Outreach Plan; 2011-10-01 10: Benchmarks & Indicators Outreach Plan; 2011-11-01 14: Regional Forecast & Virtual Present; 2012-01-01 9: Trend Future - Case Studies Comment - Summit Agenda; 2012-02-01 13: Trend Future Messaging; 2012-03-01 12: Approve Case Studies Trend Model Results; 2012-04-01 9: Workshop Strategies; 2012-06-01 11: Case Studies - Draft Community Elements; 2012-07-01 7: Workshop Marerials review; 2012-09-01 3: Test Workshop with Executive Committee; 2012-12-01 17: Workshop Results; 2013-01-01 14: Emerging Scenarios; 2013-02-01 11: Model Results - Emerging Vision; 2013-03-01 18: Regional Vision; 2013-04-01 15: Blueprint Organization; 2013-06-01 17: Demmonstration Project Seletion; 2013-07-01 29: Regional Pact; 2013-09-01 23: Review Demonstratio Projects - Toolbox Comments; 2013-11-01 18: Regional Implementation Toolbox; 2014-01-01 13: Regional Cooperative Agreement
| Executive Committee Meetings |  | 2011-03-01 28: *; 2011-04-01 18: *; 2011-05-01 16: *; 2011-06-01 13: *; 2011-07-01 11: *; 2011-07-01 25: *; 2011-09-01 12: *; 2011-10-01 10: *; 2011-11-01 14: *; 2012-01-01 9: *; 2012-02-01 13: *; 2012-03-01 12: *; 2012-04-01 9: *; 2012-05-01 14: *; 2012-06-01 11: *; 2012-07-01 7: *; 2012-09-01 3: *; 2012-09-01 17: Regional Workshops; 2012-12-01 17: *; 2013-01-01 14: *; 2013-02-01 11: *; 2013-03-01 18: *; 2013-04-01 15: *; 2013-06-01 17: *; 2013-07-01 29: *; 2013-09-01 23: *; 2013-11-01 18: *; 2014-01-01 13: *
Task 1: Build Collaborative Partnerships
| Task 1.1 | Continue Developing Regional Partnership
| Task 1.2 | Identify Opportunities to Enhance Collaboration
| Task 1.3 | State and Regional Coordination
| Task 1.4 | Strategies for Regional Collaboration
| Task 1.5 | Expand Participation
Task 2: Regional Resource Library and Scorecard
| Task 2.1 | National Research | 2011-07-01 25: Present National Research
| Task 2.2 | Survey and Integrate Regional Values | bar: 2011-07-01 18 to 2011-08-01 22; 2011-09-01 5 to 2011-10-01 3
| Task 2.3 | Data Warehouse
| Task 2.4 | Demographic Forecasts | 2011-10-01 24: Forecast Options; 2011-11-01 14: Present Final Forecast
| Task 2.5 | Regional Housing Assessment | 2011-11-01 14: Regional Housing Assessment
| Task 2.6 | Virtual Present | bar: 2011-09-01 5 to 2011-11-01 14
| Task 2.7 | Existing Conditions Analysis and Modeling | 2012-01-01 9: Trend Future
| Task 2.8 | Trend Future | 2012-02-01 13: Model Results
| Task 2.9 | Model Trend | bar: 2012-01-01 9 to 2012-02-01 13
| Task 2.10 | Develop Range of Regional Indicators for Scorecard | bar: 2012-01-01 9 to 2012-02-01 13
| Task 2.11 | Select Indicators for Scorecard, Review with Executive Committee | 2011-09-01 5: Local Indicators (Draft); 2011-10-01 17: Indicators (Final); 2011-11-01 28: Model integration; 2012-03-01 12: Refinements
| Task 2.12 | Integrate Scorecard Indicators in Modeling Efforts | bar: 2011-07-01 25 to 2012-04-01 16
| Task 2.13 | Ongoing Monitoring Program | bar: 2013-02-01 11 to 2014-02-01 24
Task 3: Conduct Public Engagement |  |  | 2011-08-01 29: Draft Outreach; 2011-10-01 3: Final Outreach Program Presentation
| Task 3.1 | Create Outreach and Engagement Strategy | bar: 2011-06-01 13 to 2011-10-01 3
| Task 3.2 | Refine and Implement Phased Outreach Strategy | bar: 2012-01-01 16 to 2012-09-01 3; 2012-12-01 17 to 2014-02-01 24
| Task 3.3 | Web Site and Template Materials (including Regional Scorecard)
| Task 3.4 | Regional Values Polling | 2011-09-01 26: Regional Summit - Peer Regions Presentation; 2012-02-01 20: Regional Summit - Existing Conditions and Trend Future; 2012-09-01 19: Regional Summit - Where Do We Want To Go?; 2013-04-01 8: Preferred Scenario - How Do We Get There?; 2014-01-01 20: Regional Vision Adoption
| Task 3.5 | Regional Scenario Workshops and Summits | bar: 2011-09-01 26; 2012-02-01 20; 2012-09-01 19; 2013-04-01 8; 2014-01-01 20
| Task 3.6 | Develop a Speakers Bureau | bar: 2011-10-01 3 to 2014-02-01 24
Task 4: Enhance Regional Leadership and Technical Capacity | bar: 2011-06-01 13 to 2014-02-01 24
| Task 4.1 | Develop Capacity-Building Strategy | bar: 2011-06-01 13 to 2011-10-01 17
| Task 4.2 | Asset Mapping | bar: 2011-08-01 29 to 2012-02-01 13
| Task 4.3 | Develop Regional Leadership Program | bar: 2011-07-01 3 to 2011-09-01 26
| Task 4.4 | Best Practices | bar: 2011-08-01 1 to 2014-02-01 24
Task 5: Develop Regional Vision | bar: 2012-02-01 13 to 2013-04-01 8
| Task 5.1 | Develop Workshop Framework and Content | 2012-02-01 13: Case Study Selection
| Task 5.2 | Workshop Training with Partners | 2012-09-01 19: Refinements
| Task 5.3 | Regional Workshops | 2012-09-01 17: Regional Workshops; 2012-12-01 24: Workshop Results
| Task 5.4 | Compile and Analyze Workshop Results | bar: 2012-10-01 22 to 2012-12-01 17
| Task 5.5 | Create Alternative Future Scenarios | 2013-01-01 21: Emerging Scenarios
| Task 5.6 | Evaluate Model Scenarios, Present Findings | 2013-02-01 18: Model Results - Emerging Vision
| Task 5.7 | Outreach Program and Regional Dialogue | 2013-03-01 11: Community Feedback
| Task 5.8 | Choose and Model Preferred Scenario | 2013-03-01 25: Preferred Scenario
| Task 5.9 | Create Vision Plan | 2013-04-01 15: Regional Vision
Task 6: Develop Regional Blueprint | bar: 2013-03-01 4 to 2014-02-01 10
| Task 6.1 | Develop Vision Framework | 2013-04-01 22: Draft Vision Framework
| Task 6.2 | Develop Blueprint Integration Strategy | 2013-05-01 20: Vision Strategy
| Task 6.3 | Identify Paths to Implementation | 2013-06-01 17: Paths to Implementation
Task 7: Begin Implementation | bar: 2013-02-01 11 to 2014-02-01 24
| Task 7.1 | Vision Adoption | bar: 2013-08-01 12 to 2014-01-01 20
| Task 7.2 | Integrate Regional Blueprint into Strategic Planning | 2013-06-01 17: Vision Integration Strategies; 2013-08-01 5: Draft Regional Pact
| Task 7.3 | Identify, Scope and Implement Demonstration Projects | 2013-06-01 17: Select Projects; 2013-09-01 30: Interim Reports; 2014-01-01 13: Demonstration Project Reports
| Task 7.4 | Create a Regional Tool Box | 2013-02-01 18: Regional Tool Box Initiation; 2013-08-01 5: Progress Report; 2013-09-01 30: Progress Report; 2013-11-01 25: Final Draft; 2014-01-01 13: Final; 2014-01-01 27: Update Continuously
| Task 7.5 | Refine and Update Regional Blueprint | bar: 2013-07-01 29 to 2014-02-01 24

## HUD Budget
INPUT
|  |  | CHECK | [5 empty] | 13.41% |  |  |  | 57.18%
|  | Task | HUD | HUD | SFRPC | SFRPC |  |  | TCRPC | TCRPC |  |  | CONSULTANTS | CONSULTANTS |  |  | TOTAL | TOTAL
|  | Proportion | Grant | Grant | [12 empty] | In-Kind | Grant + In-Kind
|  | 100% | 4250000 | Spent to Date | 1250000 | Expensed to Date |  |  | 570000 | Expensed to Date |  |  | 2430000 | Expensed to Date |  |  | 2354403 | 6604403
|  | CHECK | 4250000 | (Date) | 1250000 | Spent To Date | % of task completed | Estimated Cost to Complete | 570000 | Spent To Date | % of task completed | Estimated Cost to Complete | 2430000 | Spent To Date | % of task completed | Estimated Cost to Complete | 2354403
0%
Task S1 | Governance, Organization |  | 6375 |  | 4781.25 |  |  |  | 1593.75 |  |  |  | 0
Task S2 | Work Plan Development |  | 6375 |  | 4781.25 |  |  |  | 1593.75 |  |  |  | 0
Task S3 | Consortium Agreements |  | 12750 |  | 9562.5 |  |  |  | 3187.5 |  |  |  | 0
Task S4 | Recruit Staff |  | 12750 |  | 9562.5 |  |  |  | 3187.5 |  |  |  | 0
Task S5 | Form and Operationalize Work Groups and Committees |  | 12750 |  | 9562.5 |  |  |  | 3187.5 |  |  |  | 0
Task S6 | Initiate Early Stages of Activities |  | 12750 |  | 9562.5 |  |  |  | 3187.5 |  |  |  | 0
Task S7 | Develop RFP(s) |  | 63750 |  | 47812.5 |  |  |  | 15937.5 |  |  |  | 0
|  | 3% | 127500 |  | 95625 |  |  |  | 31875 |  |  |  | 0 |  |  |  | 70632.09 | 198132.09
0%
Task 1.1 | Continue Developing Regional Partnership |  | 51000 |  | 38250 |  |  |  | 12750 |  |  |  | 0
Task 1.2 | Identify Opportunities to Enhance Collaboration |  | 51000 |  | 38250 |  |  |  | 12750 |  |  |  | 0
Task 1.3 | State and Regional Coordination |  | 51000 |  | 38250 |  |  |  | 12750 |  |  |  | 0
Task 1.4 | Strategies for Regional Collaboration |  | 51000 |  | 38250 |  |  |  | 12750 |  |  |  | 0
Task 1.5 | Expand Participation |  | 51000 |  | 38250 |  |  |  | 12750 |  |  |  | 0
|  | 6% | 255000 |  | 191250 |  |  |  | 63750 |  |  |  | 0 |  |  |  | 141264.18 | 396264.18
38% total RPCs
Task 2.1 | National Research |  | 23975 | 4000 |  |  |  |  | 4000 |  |  |  | 19975
Task 2.2 | Survey and Integrate Regional Values |  | 39950 | 0 | [8 empty] | 39950
Task 2.3 | Data Warehouse |  | 143650 | 0 | [8 empty] | 143650
Task 2.4 | Demographic Forecasts |  | 56313 | 36338 | 36338 | [7 empty] | 19975
Task 2.5 | Regional Housing Assessment |  | 152325 | 68600 | 48450 |  |  |  | 20150 |  |  |  | 83725
Task 2.6 | Virtual Present |  | 108375 | 48450 | 48450 | [7 empty] | 59925
Task 2.7 | Existing Conditions Analysis and Modeling |  | 52440 | 4500 |  |  |  |  | 4500 |  |  |  | 47940
Task 2.8 | Trend Future |  | 64076 | 16136 | 12111 |  |  |  | 4025 |  |  |  | 47940
Task 2.9 | Model Trend |  | 15985 | 4000 | 0 |  |  |  | 4000 |  |  |  | 11985
Task 2.10 | Develop Range of Regional Indicators for Scorecard |  | 90038 | 50088 | 36338 |  |  |  | 13750 |  |  |  | 39950
Task 2.11 | Select Indicators for Scorecard and Review with Executive Committee |  | 54083 | 50088 | 36338 |  |  |  | 13750 |  |  |  | 3995
Task 2.12 | Integrate Scorecard Indicators in Modeling Efforts |  | 7990 | 0 | 0 | [7 empty] | 7990
Task 2.13 | Ongoing Monitoring Program |  | 40800 | 40800 | 24225 |  |  |  | 16575 |  |  |  | 0
|  | 20% | 850000 | 323000 | 242250 |  |  |  | 80750 |  |  |  | 527000 |  |  |  | 470880.6 | 1320880.6
Task 3.1 | Create Outreach and Engagement Strategy (including Work gorups) |  | 99250 | 10000 |  |  |  |  | 10000 |  |  |  | 89250
Task 3.2 | Refine and Implement Phased Outreach Strategy |  | 202343.5 | 52531 | 43031 |  |  |  | 9500 |  |  |  | 149812.5
Task 3.3 | Web Site and Template Materials (including Regional Scorecard) |  | 10563 | 10563 | 9563 |  |  |  | 1000 |  |  |  | 0
Task 3.4 | Regional Values Polling |  | 100388 | 11138 | 9563 |  |  |  | 1575 |  |  |  | 89250
Task 3.5 | Regional Scenario Workshops and Summits (including work groups) |  | 214093.5 | 32406 | 23906 |  |  |  | 8500 |  |  |  | 181687.5
Task 3.6 | Develop a Speakers Bureau |  | 10862 | 10862 | 9562 |  |  |  | 1300 |  |  |  | 0
|  | 15% | 637500 | 127500 | 95625 |  |  |  | 31875 |  |  |  | 510000 |  |  |  | 353160.45 | 990660.45
Task 4.1 | Develop Capacity-Building Strategy |  | 54992 | 54992 | 52992 |  |  |  | 2000 |  |  |  | 0
Task 4.2 | Asset Mapping |  | 91429.5 | 83992 | 52992 |  |  |  | 31000 |  |  |  | 7437.5
Task 4.3 | Develop Regional Leadership Program |  | 94222.5 | 86785 | 84788 |  |  |  | 2000 |  |  |  | 7437.5
Task 4.4 | Best Practices |  | 56856 | 56856 | 21196 |  |  |  | 35660 |  |  |  | 0
|  | 7% | 297500 | 282625 | 211968 |  |  |  | 70660 |  |  |  | 14875 |  |  |  | 164808.21 | 462308.21
Task 5.1 | Develop Workshop Framework and Content |  | 63751.5 | 15939 | 11954 |  |  |  | 3984.75 |  |  |  | 47812.5
Task 5.2 | Workshop Training with Partners |  | 39047.75 | 11954 | 11954 | [7 empty] | 27093.75
Task 5.3 | Regional Workshops |  | 192622 | 58747 | 47810 |  |  |  | 10937 |  |  |  | 133875
Task 5.4 | Compile and Analyze Workshop Results |  | 43937.5 | 2500 |  |  |  |  | 2500 |  |  |  | 41437.5
Task 5.5 | Create Alternative Future Scenarios |  | 123517.75 | 19924 | 11954 |  |  |  | 7970 |  |  |  | 103593.75
Task 5.6 | Evaluate Model Scenarios, Present Findings |  | 23218.75 | 2500 |  |  |  |  | 2500 |  |  |  | 20718.75
Task 5.7 | Outreach Program and Regional Dialogue |  | 15937 | 15937 | 11954 |  |  |  | 3984.25 |  |  |  | 0
Task 5.8 | Choose and Model Preferred Scenario |  | 57374.5 | 15937 | 11954 |  |  |  | 3984.25 |  |  |  | 41437.5
Task 5.9 | Develop Vision and Blueprint Framework |  | 78093.25 | 15937 | 11954 |  |  |  | 3984.25 |  |  |  | 62156.25
|  | 15% | 637500 | 159375 | 119534 |  |  |  | 39844.5 |  |  |  | 478125 |  |  |  | 353160.45 | 990660.45
Task 5.10 | Create Vision and Blueprint Plan |  | 160650 | 84150 | 63112 |  |  |  | 21037.5 |  |  | 25000 | 51500
Task 5.11 | Develop 5-year Implementation Plan |  | 174675 | 98175 | 71136 |  |  |  | 27039 |  |  | 25000 | 51500
Task 5.12 | Identify Paths to Implementation |  | 174675 | 98175 | 73631.25 |  |  |  | 24543.75 |  |  | 25000 | 51500
|  | 12% | 510000 | 280500 | 207879.25 |  |  |  | 72620.25 |  |  | 75000 | 154500 |  |  |  | 282528.36 | 792528.36
TCRPC Amend.
Task 6.1 | Vision Adoption |  | 74075 | 24075 | 17175 |  |  |  | 6900 |  |  | 50000 | 0
Task 6.2 | Integrate Regional Blueprint into Strategic Planning |  | 39075 | 24075 | 17175 |  |  |  | 6900 |  |  | 15000 | 0
Task 6.3 | Identify, Scope and Implement Demonstration Projects |  | 680080 | 14098 | 8588 |  |  |  | 5510 |  |  | 10000 | 655982
Task 6.4 | Create a Regional Tool Box |  | 118870 | 29352 | 25762 |  |  |  | 3590 |  |  |  | 89518
Task 6.5 | Refine and Update Regional Blueprint |  | 22900 | 22900 | 17175 |  |  |  | 5725 |  |  |  | 0
|  | 22% | 935000 | 114500 | 85875 |  |  |  | 28625 |  |  | 75000 | 745500 |  |  |  | 517968.66 | 1452968.66
0

## Budget Details
INPUT
[6 empty] | 100% | 39.29% | 36% | 24.71% | 60.71% | Percent of Overall Grant to RPCs, Prime Contractor, Sub-Grants / Local Contractors
[6 empty] | CHECK | 39.29% | 36% | 24.71% | 60.71%
[5 empty] | Assumed | HUD | SFRPC | Prime | Consultants | Consultants | TOTAL | Assumed | SFRPC | Prime | Consultants
[5 empty] | Proportion | Grant | TCRPC | Consultant | Sub-Grants | Sub-Grants | In-Kind | Proportion | TCRPC | Consultant | Sub-Grants
[5 empty] | 100% | 4250000 | 1670000 | 1530000 | 1050000 | 2580000 | 2354403 | 100%
[5 empty] | CHECK | 4250000 | 1670000 | 1530000 | 1050000 | 2580000
Scoping Phase | [6 empty] | 100% | 0% | 0% | 0% | 100% |  | 100% | 0% | 0%
| Task S1 | Governance, Organization |  |  |  |  | 6375 |  |  | 0 |  |  | 5%
| Task S2 | Work Plan Development |  |  |  |  | 6375 |  |  | 0 |  |  | 5%
| Task S3 | Consortium Agreements |  |  |  |  | 12750 |  |  | 0 |  |  | 10%
| Task S4 | Recruit Staff |  |  |  |  | 12750 |  |  | 0 |  |  | 10%
| Task S5 | Form and Operationalize Work Groups and Committees |  |  |  |  | 12750 |  |  | 0 |  |  | 10%
| Task S6 | Initiate Early Stages of Activities |  |  |  |  | 12750 |  |  | 0 |  |  | 10%
|  | S6.1 | Web Site Launch | [6 empty] | 0
|  | S6.2 | Initiate Technical Work | [6 empty] | 0
| Task S7 | Develop RFP(s) |  |  |  |  | 63750 |  |  | 0 |  |  | 50%
TOTAL Scoping Phase |  |  | Percent of Phase |  | 3% | 127500 | 127500 | 0 | 0 | 0 | 70632.09 | 3%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts
Task 1: Build Collaborative Partnerships | [6 empty] | 100% | 0% | 0% | 0% |  |  | 100%
| Task 1.1 | Continue Developing Regional Partnership |  |  |  |  | 51000 | [5 empty] | 20%
| Task 1.2 | Identify Opportunities to Enhance Collaboration |  |  |  |  | 51000 | [5 empty] | 20%
| Task 1.3 | State and Regional Coordination |  |  |  |  | 51000 | [5 empty] | 20%
| Task 1.4 | Strategies for Regional Collaboration |  |  |  |  | 51000 | [5 empty] | 20%
| Task 1.5 | Expand Participation |  |  |  |  | 51000 | [5 empty] | 20%
TOTAL Task 1 |  |  |  |  | 6% | 255000 | 255000 | 0 | 0 | 0 | 141264.18 | 6%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts |  |  |  | 100% | 100% | 100%
Task 2: Regional Resource Library and Scorecard |  |  |  | 0% |  |  | 38% | 47% | 15% | 62%
| Task 2.1 | National Research |  |  |  |  | 0 | 19975 |  | 19975 |  |  |  | 5%
| Task 2.2 | Survey and Integrate Regional Values | [5 empty] | 39950 |  | 39950 |  |  |  | 10%
| Task 2.3 | Data Warehouse | [5 empty] | 79900 | 63750 | 143650 |  |  |  | 20% | 50%
|  | 2.3.1 | Environmental Plans | [6 empty] | 0
|  | 2.3.2 | Compile and Interpret Comprehensive Plans / Parcels | [6 empty] | 0
|  | 2.3.3 | Sea Level Change Impacts | [6 empty] | 0
|  | 2.3.4 | Jobs/Housing Balance, Jobs/Housing Match | [6 empty] | 0
|  | 2.3.5 | Finalize Scenario Working Files | [6 empty] | 0
|  | 2.3.6 | Vacant Land Inventory | [6 empty] | 0
| Task 2.4 | Demographic Forecasts |  |  |  |  | 48450 | 19975 |  | 19975 |  |  | 15% | 5%
| Task 2.5 | Regional Housing Assessment |  |  |  |  | 64600 | 19975 | 63750 | 83725 |  |  | 20% | 5% | 50%
| Task 2.6 | Virtual Present |  |  |  |  | 64600 | 59925 |  | 59925 |  |  | 20% | 15%
|  | 2.6.1 | Redevelopment Potential | [6 empty] | 0
|  | 2.6.2 | Land Suitability Index | [6 empty] | 0
|  | 2.6.3 | Infrastructure Assessment | [6 empty] | 0
|  | 2.6.4 | Transportation Network and Transit Accessibility | [6 empty] | 0
|  | 2.6.5 | Housing & Employment Distribution | [6 empty] | 0
|  | 2.6.6 | Energy Audit / Budget | [6 empty] | 0
|  | 2.6.7 | Human System Interface
| Task 2.7 | Existing Conditions Analysis and Modeling | [5 empty] | 47940 |  | 47940 |  |  |  | 12%
| Task 2.8 | Trend Future |  |  |  |  | 16150 | 47940 |  | 47940 |  |  | 5% | 12%
| Task 2.9 | Model Trend | [5 empty] | 11985 |  | 11985 |  |  |  | 3%
| Task 2.10 | Develop Range of Regional Indicators for Scorecard |  |  |  |  | 48450 | 39950 |  | 39950 |  |  | 15% | 10%
| Task 2.11 | Select Indicators for Scorecard and Review with Executive Committee |  |  |  |  | 48450 | 3995 |  | 3995 |  |  | 15% | 1%
| Task 2.12 | Integrate Scorecard Indicators in Modeling Efforts | [5 empty] | 7990 |  | 7990 |  |  |  | 2%
| Task 2.13 | Ongoing Monitoring Program |  |  |  |  | 32300 |  |  | 0 |  |  | 10%
TOTAL Task 2 |  |  |  |  | 20% | 850000 | 323000 | 399500 | 127500 | 527000 | 470880.6 | 20%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts
Task 3: Conduct Public Engagement | [6 empty] | 20% | 70% | 10% | 80% |  |  | 90% | 100% | 100%
| Task 3.1 | Create Outreach and Engagement Strategy | [5 empty] | 89250 | 0 | 89250 |  |  |  | 20%
| Task 3.2 | Refine and Implement Phased Outreach Strategy |  |  |  |  | 57375 | 133875 | 15937.5 | 149812.5 |  |  | 45% | 30% | 25%
|  | 3.2.1 | Trend Outreach | [6 empty] | 0
|  | 3.2.2 | Scenarios Outreach | [6 empty] | 0
|  | 3.2.3 | Vision Outreach | [6 empty] | 0
| Task 3.3 | Web Site and Template Materials (including Regional Scorecard) |  |  |  |  | 12750 |  |  | 0 |  |  | 10%
| Task 3.4 | Regional Values Polling |  |  |  |  | 12750 | 89250 |  | 89250 |  |  | 10% | 20%
| Task 3.5 | Regional Scenario Workshops and Summits |  |  |  |  | 31875 | 133875 | 47812.5 | 181687.5 |  |  | 25% | 30% | 75%
| Task 3.6 | Develop a Speakers Bureau |  |  |  |  | 12750 | [5 empty] | 10%
TOTAL Task 3 |  |  |  |  | 15% | 637500 | 127500 | 446250 | 63750 | 510000 | 353160.45 | 15%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts
Task 4: Enhance Regional Leadership and Technical Capacity | [6 empty] | 95% |  | 5% | 5% |  |  | 100% |  | 100%
| Task 4.1 | Develop Capacity-Building Strategy |  |  |  |  | 70656.25 |  |  | 0 |  |  | 25%
| Task 4.2 | Asset Mapping |  |  |  |  | 70656.25 |  | 7437.5 | 7437.5 |  |  | 25% |  | 50%
| Task 4.3 | Develop Regional Leadership Program |  |  |  |  | 113050 |  | 7437.5 | 7437.5 |  |  | 40% |  | 50%
| Task 4.4 | Best Practices |  |  |  |  | 28262.5 |  |  | 0 |  |  | 10%
TOTAL Task 4 |  |  |  |  | 7% | 297500 | 282625 | 0 | 14875 | 14875 | 164808.21 | 7%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts
Task 5: Develop Regional Vision | [6 empty] | 25% | 65% | 10% | 75% |  |  | 100% | 100% | 100%
| Task 5.1 | Develop Workshop Framework and Content |  |  |  |  | 15937.5 |  | 47812.5 | 47812.5 |  |  | 10% |  | 75%
|  | 5.1.1 | Case Studies - Examples of Good Growth in the Region | [6 empty] | 0
|  | 5.1.2 | Workshop Base & Materials | [6 empty] | 0
| 0 | 5.1.3 | Test Workshop with Executive Committee |  |  |  | 0 | 0 |  | 0 |  |  | 0% | 0%
| Task 5.2 | Workshop Training with Partners |  |  |  |  | 15937.5 | 20718.75 | 6375 | 27093.75 |  |  | 10% | 5% | 10%
| Task 5.3 | Regional Workshops |  |  |  |  | 63750 | 124312.5 | 9562.5 | 133875 |  |  | 40% | 30% | 15%
| Task 5.4 | Compile and Analyze Workshop Results | [5 empty] | 41437.5 |  | 41437.5 |  |  |  | 10%
| Task 5.5 | Create Alternative Future Scenarios |  |  |  |  | 15937.5 | 103593.75 |  | 103593.75 |  |  | 10% | 25%
| Task 5.6 | Evaluate Model Scenarios, Present Findings | [5 empty] | 20718.75 |  | 20718.75 |  |  |  | 5%
| Task 5.7 | Outreach Program and Regional Dialogue |  |  |  |  | 15937.5 | 0 |  | 0 |  |  | 10%
| Task 5.8 | Choose and Model Preferred Scenario |  |  |  |  | 15937.5 | 41437.5 |  | 41437.5 |  |  | 10% | 10%
| Task 5.9 | Create Vision Plan |  |  |  |  | 15937.5 | 62156.25 |  | 62156.25 |  |  | 10% | 15%
TOTAL Task 5 |  |  |  |  | 15% | 637500 | 159375 | 414375 | 63750 | 478125 | 353160.45 | 15%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts
Task 6: Develop Regional Blueprint | [6 empty] | 55% | 38% | 7% | 45% |  |  | 100% | 100% | 100%
| Task 6.1 | Develop Vision Framework |  |  |  |  | 84150 | 58140 | 10710 | 68850 |  |  | 30% | 30% | 30%
| Task 6.2 | Develop Blueprint Integration Strategy |  |  |  |  | 98175 | 67830 | 12495 | 80325 |  |  | 35% | 35% | 35%
| Task 6.3 | Identify Paths to Implementation |  |  |  |  | 98175 | 67830 | 12495 | 80325 |  |  | 35% | 35% | 35%
TOTAL Task 6 |  |  |  |  | 12% | 510000 | 280500 | 193800 | 35700 | 229500 | 282528.36 | 12%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts
Task 7: Begin Implementation | [6 empty] | 12.25% | 8.136% | 79.62% | 87.75% |  |  | 100% | 100% | 100%
| Task 7.1 | Vision Adoption |  |  |  |  | 22900 |  |  | 0 |  |  | 20%
| Task 7.2 | Integrate Regional Blueprint into Strategic Planning |  |  |  |  | 22900 |  |  | 0 |  |  | 20%
| Task 7.3 | Identify, Scope and Implement Demonstration Projects |  |  |  |  | 11450 | 19018.75 | 707203.75 | 726222.5 |  |  | 10% | 25% | 95%
| Task 7.4 | Create a Regional Tool Box |  |  |  |  | 34350 | 57056.25 | 37221.25 | 94277.5 |  |  | 30% | 75% | 5%
| Task 7.5 | Refine and Update Regional Blueprint |  |  |  |  | 22900 |  |  | 0 |  |  | 20%
TOTAL Task 7 |  |  |  |  | 22% | 935000 | 114500 | 76075 | 744425 | 820500 | 517968.66 | 22%
[5 empty] | % Total |  | RPC | Prime | Sub-Contracts

## Work Plan Detail
SE Florida Regional Vision and Blueprint Work Plan | [13 empty] | Where Are We Now? | [24 empty] | Where Are We Now? | [12 empty] | Where Are We Going? | [13 empty] | Where Are We Going? | [21 empty] | Where Do We Want To Go? | [16 empty] | How Do We Get There? | [10 empty] | How Do We Get There? | [30 empty] | How Do We Get There?
Detailed Tasks |  |  |  | 2011-02-01 |  |  |  | 2011-03-01 |  |  |  | 2011-04-01 |  |  |  | 2011-05-01 |  |  |  |  | 2011-06-01 |  |  |  | 2011-07-01 |  |  |  | 2011-08-01 |  |  |  |  | 2011-09-01 |  |  |  | 2011-10-01 |  |  |  |  | 2011-11-01 |  |  |  | 2011-12-01 |  |  |  | 2012-01-01 |  |  |  |  | 2012-02-01 |  |  |  | 2012-03-01 |  |  |  | 2012-04-01 |  |  |  |  | 2012-05-01 |  |  |  | 2012-06-01 |  |  |  | 2012-07-01 |  |  |  |  | 2012-08-01 |  |  |  | 2012-09-01 |  |  |  | 2012-10-01 |  |  |  |  | 2012-11-01 |  |  |  | 2012-12-01 |  |  |  |  | 2013-01-01 |  |  |  | 2013-02-01 |  |  |  | 2013-03-01 |  |  |  | 2013-04-01 |  |  |  |  | 2013-05-01 |  |  |  | 2013-06-01 |  |  |  | 2013-07-01 |  |  |  |  | 2013-08-01 |  |  |  | 2013-09-01 |  |  |  |  | 2013-10-01 |  |  |  | 2013-11-01 |  |  |  | 2013-12-01 |  |  |  |  | 2014-01-01 |  |  |  | 2014-02-01
|  |  |  | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 7 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 19 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
Scoping Phase |  |  |  | 2011-02-01 21: HUD Agreement; 2011-04-01 18: 60 Days; 2011-06-01 20: 120 Days
| Task S1 | Governance, Organization | bar: 2011-02-01 7 to 2011-05-01 9
| Task S2 | Work Plan Development | bar: 2011-02-01 21 to 2011-04-01 18
| Task S3 | Consortium Agreements | bar: 2011-04-01 4 to 2011-06-01 20
| Task S4 | Recruit Staff | bar: 2011-04-01 4 to 2011-04-01 25; 2011-05-01 23
| Task S5 | Form and Operationalize Work Groups and Committees | bar: 2011-04-01 18 to 2011-06-01 20
| Task S6 | Initiate Early Stages of Activities | bar: 2011-04-01 18 to 2011-06-01 20
|  | S6.1 | Web Site Launch | bar: 2011-04-01 18 to 2011-06-01 20
|  | S6.2 | Initiate Technical Work | bar: 2011-04-01 18 to 2011-06-01 20
| Task S7 | Develop RFP(s) | bar: 2011-05-01 23 to 2011-07-01 11
Governance and Consortium Building |  |  |  | 2011-09-01 26: Regional Summit - Peer Regions Presentation; 2012-02-01 20: Regional Summit - Existing Conditions and Trend Future; 2012-09-01 19: Regional Summit - Where Do We Want To Go?; 2013-04-01 8: Preferred Scenario - How Do We Get There?; 2014-01-01 20: Regional Vision Adoption
Regioinal Summits | bar: 2011-09-01 26; 2012-02-01 20; 2012-09-01 19; 2013-04-01 8; 2014-01-01 20
| Leadership Development, Identify Champions, Local Government Outreach |  |  | 2011-03-01 28: Convene Committee - Staff Positions - Draft Work Plan; 2011-04-01 18: Staff Position Approval; 2011-05-01 16: Final Committees & Work Plan Approval; 2011-06-01 13: Consortium Agreements RFP Approval; 2011-07-01 11: Interview & Appoint Consultant; 2011-07-01 25: Visioning exercise with Executive Committee; 2011-09-01 12: Summit Approval - Polling Results - Outreach Plan; 2011-10-01 10: Benchmarks & Indicators Outreach Plan; 2011-11-01 14: Regional Forecast & Virtual Present; 2012-01-01 9: Trend Future - Case Studies Comment - Summit Agenda; 2012-02-01 13: Trend Future Messaging; 2012-03-01 12: Approve Case Studies Trend Model Results; 2012-04-01 9: Workshop Strategies; 2012-06-01 11: Case Studies - Draft Community Elements; 2012-07-01 7: Workshop Marerials review; 2012-09-01 3: Test Workshop with Executive Committee; 2012-12-01 17: Workshop Results; 2013-01-01 14: Emerging Scenarios; 2013-02-01 11: Model Results - Emerging Vision; 2013-03-01 18: Regional Vision; 2013-04-01 15: Blueprint Organization; 2013-06-01 17: Demmonstration Project Seletion; 2013-07-01 29: Regional Pact; 2013-09-01 23: Review Demonstratio Projects - Toolbox Comments; 2013-11-01 18: Regional Implementation Toolbox; 2014-01-01 13: Regional Cooperative Agreement
| Executive Committee Meetings |  |  | 2011-03-01 28: *; 2011-04-01 18: *; 2011-05-01 16: *; 2011-06-01 13: *; 2011-07-01 11: *; 2011-07-01 25: *; 2011-09-01 12: *; 2011-10-01 10: *; 2011-11-01 14: *; 2012-01-01 9: *; 2012-02-01 13: *; 2012-03-01 12: *; 2012-04-01 9: *; 2012-05-01 14: *; 2012-06-01 11: *; 2012-07-01 7: *; 2012-09-01 3: *; 2012-09-01 17: Regional Workshops; 2012-12-01 17: *; 2013-01-01 14: *; 2013-02-01 11: *; 2013-03-01 18: *; 2013-04-01 15: *; 2013-06-01 17: *; 2013-07-01 29: *; 2013-09-01 23: *; 2013-11-01 18: *; 2014-01-01 13: *
Task 1: Build Collaborative Partnerships
| Task 1.1 | Continue Developing Regional Partnership
| Task 1.2 | Identify Opportunities to Enhance Collaboration
| Task 1.3 | State and Regional Coordination
| Task 1.4 | Strategies for Regional Collaboration
| Task 1.5 | Expand Participation
Task 2: Regional Resource Library and Scorecard
| Task 2.1 | National Research |  | 2011-07-01 25: Present National Research
| Task 2.2 | Survey and Integrate Regional Values | bar: 2011-07-01 18 to 2011-08-01 22; 2011-09-01 5 to 2011-10-01 3
| Task 2.3 | Data Warehouse
|  | 2.3.1 | Environmental Plans | bar: 2011-06-01 13 to 2011-06-01 27
|  | 2.3.2 | Compile and Interpret Comprehensive Plans / Parcels | 2011-08-01 1: Progress Report
|  | 2.3.3 | Sea Level Change Impacts | 2011-09-01 26: Progress Report
|  | 2.3.4 | Jobs/Housing Balance, Jobs/Housing Match | bar: 2011-07-01 18 to 2011-09-01 26
|  | 2.3.5 | Finalize Scenario Working Files | 2011-10-01 24: Vacant Land Inventory
|  | 2.3.6 | Vacant Land Inventory | bar: 2011-09-01 26 to 2011-10-01 24
| Task 2.4 | Demographic Forecasts |  | 2011-10-01 24: Forecast Options; 2011-11-01 14: Present Final Forecast
| Task 2.5 | Regional Housing Assessment |  | 2011-11-01 14: Regional Housing Assessment
| Task 2.6 | Virtual Present | bar: 2011-09-01 5 to 2011-11-01 14
|  | 2.6.1 | Redevelopment Potential | bar: 2011-09-01 19 to 2011-11-01 14
|  | 2.6.2 | Land Suitability Index | bar: 2011-09-01 26 to 2011-11-01 14
|  | 2.6.3 | Infrastructure Assessment | bar: 2011-10-01 3 to 2011-11-01 14
|  | 2.6.4 | Transportation Network and Transit Accessibility | bar: 2011-10-01 10 to 2011-11-01 14
|  | 2.6.5 | Housing & Employment Distribution | bar: 2011-10-01 31 to 2011-11-01 14
|  | 2.6.6 | Energy Audit / Budget | bar: 2011-10-01 31 to 2011-11-01 14
|  | 2.6.7 | Human System Interface | bar: 2011-10-01 31 to 2011-11-01 14
| Task 2.7 | Existing Conditions Analysis and Modeling |  | 2012-01-01 9: Trend Future
| Task 2.8 | Trend Future |  | 2012-02-01 13: Model Results
| Task 2.9 | Model Trend | bar: 2012-01-01 9 to 2012-02-01 13
| Task 2.10 | Develop Range of Regional Indicators for Scorecard | bar: 2012-01-01 9 to 2012-02-01 13
| Task 2.11 | Select Indicators for Scorecard and Review with Executive Committee |  | 2011-09-01 5: Local Indicators (Draft); 2011-10-01 17: Indicators (Final); 2011-11-01 28: Model integration; 2012-03-01 12: Refinements
| Task 2.12 | Integrate Scorecard Indicators in Modeling Efforts | bar: 2011-07-01 25 to 2012-04-01 16
| Task 2.13 | Ongoing Monitoring Program | bar: 2013-02-01 11 to 2014-02-01 24
Task 3: Conduct Public Engagement |  |  |  | 2011-08-01 29: Draft Outreach; 2011-10-01 3: Final Outreach Program Presentation
| Task 3.1 | Create Outreach and Engagement Strategy | bar: 2011-06-01 13 to 2011-10-01 3
| Task 3.2 | Refine and Implement Phased Outreach Strategy | bar: 2012-01-01 16 to 2012-09-01 3; 2012-12-01 17 to 2014-02-01 24
|  | 3.2.1 | Trend Outreach | bar: 2012-01-01 16 to 2012-09-01 3
|  | 3.2.2 | Scenarios Outreach | bar: 2012-12-01 17 to 2013-03-01 11
|  | 3.2.3 | Vision Outreach | bar: 2013-03-01 18 to 2014-02-01 24
| Task 3.3 | Web Site and Template Materials (including Regional Scorecard)
| Task 3.4 | Regional Values Polling |  | 2011-09-01 26: Regional Summit - Peer Regions Presentation; 2012-02-01 20: Regional Summit - Existing Conditions and Trend Future; 2012-09-01 19: Regional Summit - Where Do We Want To Go?; 2013-04-01 8: Preferred Scenario - How Do We Get There?; 2014-01-01 20: Regional Vision Adoption
| Task 3.5 | Regional Scenario Workshops and Summits | bar: 2011-09-01 26; 2012-02-01 20; 2012-09-01 19; 2013-04-01 8; 2014-01-01 20
| Task 3.6 | Develop a Speakers Bureau | bar: 2011-10-01 3 to 2014-02-01 24
Task 4: Enhance Regional Leadership and Technical Capacity | bar: 2011-06-01 13 to 2014-02-01 24
| Task 4.1 | Develop Capacity-Building Strategy | bar: 2011-06-01 13 to 2011-10-01 17
| Task 4.2 | Asset Mapping | bar: 2011-08-01 29 to 2012-02-01 13
| Task 4.3 | Develop Regional Leadership Program | bar: 2011-07-01 3 to 2011-09-01 26
| Task 4.4 | Best Practices | bar: 2011-08-01 1 to 2014-02-01 24
Task 5: Develop Regional Vision | bar: 2012-02-01 13 to 2013-04-01 8
| Task 5.1 | Develop Workshop Framework and Content |  | 2012-02-01 13: Case Study Selection
|  | 5.1.1 | Case Studies - Examples of Good Growth in the Region | 2012-05-01 28: Interim Report; 2012-06-01 25: Final Report
|  | 5.1.2 | Workshop Base & Materials | 2012-08-01 27: Complete workshop package
|  | 5.1.3 | Test Workshop with Executive Committee | 2012-04-01 2: Base Map; 2012-09-01 3: Test Workshop with Committee
| Task 5.2 | Workshop Training with Partners |  | 2012-09-01 19: Refinements
| Task 5.3 | Regional Workshops |  | 2012-09-01 17: Regional Workshops; 2012-12-01 24: Workshop Results
| Task 5.4 | Compile and Analyze Workshop Results | bar: 2012-10-01 22 to 2012-12-01 17
| Task 5.5 | Create Alternative Future Scenarios |  | 2013-01-01 21: Emerging Scenarios
| Task 5.6 | Evaluate Model Scenarios, Present Findings |  | 2013-02-01 18: Model Results - Emerging Vision
| Task 5.7 | Outreach Program and Regional Dialogue |  | 2013-03-01 11: Community Feedback
| Task 5.8 | Choose and Model Preferred Scenario |  | 2013-03-01 25: Preferred Scenario
| Task 5.9 | Create Vision Plan |  | 2013-04-01 15: Regional Vision
Task 6: Develop Regional Blueprint | bar: 2013-03-01 4 to 2014-02-01 10
| Task 6.1 | Develop Vision Framework |  | 2013-04-01 22: Draft Vision Framework
| Task 6.2 | Develop Blueprint Integration Strategy |  | 2013-05-01 20: Vision Strategy
| Task 6.3 | Identify Paths to Implementation |  | 2013-06-01 17: Paths to Implementation
Task 7: Begin Implementation | bar: 2013-02-01 11 to 2014-02-01 24
| Task 7.1 | Vision Adoption | bar: 2013-08-01 12 to 2014-01-01 20
| Task 7.2 | Integrate Regional Blueprint into Strategic Planning |  | 2013-06-01 17: Vision Integration Strategies; 2013-08-01 5: Draft Regional Pact
| Task 7.3 | Identify, Scope and Implement Demonstration Projects |  | 2013-06-01 17: Select Projects; 2013-09-01 30: Interim Reports; 2014-01-01 13: Demonstration Project Reports
| Task 7.4 | Create a Regional Tool Box |  | 2013-02-01 18: Regional Tool Box Initiation; 2013-08-01 5: Progress Report; 2013-09-01 30: Progress Report; 2013-11-01 25: Final Draft; 2014-01-01 13: Final; 2014-01-01 27: Update Continuously
| Task 7.5 | Refine and Update Regional Blueprint | bar: 2013-07-01 29 to 2014-02-01 24